## Weekly Summary
PROJECT WEEKLY SUMMARY (ONE PAGE SUMMARY)
Project: Digital Platform Upgrade
PM: |  | Latha Lakshmanan |  | Report Date: | 19-Apr-2026 |  | Sprint / Week: |  | Sprint 4 | Wk | 12 | Phase: |  | Development
OVERALL STATUS: |  | 🟠 AMBER | Action Required | Timeline: | 🟠 AMBER | 1-week delay in design | Budget: |  | 🟢 GREEN | Within plan; watch EAC (+$1.5K) | Scope / Quality: |  | 🟢 GREEN | No scope changes approved
One-Line Summary: |  |  | Project is slightly delayed due to design dependency, budget risk emerging, and immediate client + sponsor decisions are required.
SNAPSHOT |  |  |  | FINANCIALS |  |  | MILESTONES |  |  |  | HEAT MAP - FOCUS AREAS
Metric |  | Value |  | Item | Amount |  | Milestone |  | Planned | Status | Area |  | Status
Progress |  | 65% Complete |  | Approved Budget | $10,000 |  | Design Sign-off |  | Jul 10 | ⚠️ Delayed | Design Approval |  | 🔴 CRITICAL
Planned vs Actual |  | -5 days ⚠️ |  | Spent to Date | $6,000 (60%) |  | Development Sprint |  | Jul 25 | ✔️ On Track | Vendor API Delivery |  | 🟠 AT RISK
Budget Spent / Total |  | $6K / $10K |  | Forecast at Completion | $11,500 ⚠️ |  | QA & Testing |  | Aug 5 | 📅 Upcoming | QA Readiness |  | 🟠 AT RISK
Forecast at Completion |  | $11,500 ⚠️ |  | Variance | +$1,500 over |  | Go Live |  | Aug 15 | 📅 Upcoming | Resource Availability |  | 🟢 ON TRACK
RISKS, ISSUES & MITIGATION (Type dropdown: Risk / Issue / Assumption)
Type | Description |  |  |  | Owner |  | Mitigation |  |  |  | Impact
🔴 Risk | Late design feedback from client |  |  |  | PM |  | Escalate; enforce Jul 12 deadline |  |  |  | Blocks Dev start
🟠 Issue | API from vendor not ready |  |  |  | Tech Lead |  | Parallel dev + vendor SLA trigger |  |  |  | Delays QA by 3–5 days
🟠 Risk | Budget overrun forecast +$1.5K |  |  |  | Sponsor |  | Scope review; phase non-essentials to v2 |  |  |  | Requires sponsor approval
DECISIONS REQUIRED — Named · Owned · Dated
Decision Needed | [5 empty] | Owner / Stakeholder |  |  |  | Deadline |  | RAG | Impact if Not Taken
Approve design sign-off | [5 empty] | Client / Design Lead |  |  |  | Jul 12 |  | 🔴 Critical | Blocks Dev Sprint (Revised from Jul 10)
Approve budget increase (+$1.5K) | [5 empty] | Sponsor |  |  |  | Jul 15 |  | 🟠 Amber | Risk to committed milestones
Confirm vendor API SLA | [5 empty] | Vendor / PM |  |  |  | Jul 18 |  | 🟠 Amber | Potential Go-Live impact
DEPENDENCIES (items blocking or waiting — all with RAG)
Dependency |  |  |  |  | Owner |  |  | Due Date |  |  | RAG | Impact if Late
Design Sign-off (hard gate) |  |  |  |  | Client |  |  | Jul 12 |  |  | 🔴 Critical | Blocks Dev sprint (Revised from Jul 10)
Vendor API readiness |  |  |  |  | Vendor |  |  | Jul 20 |  |  | 🟠 At Risk | Delays QA phase
Sponsor budget approval |  |  |  |  | Sponsor |  |  | Jul 15 |  |  | 🟠 At Risk | Scope cut risk
NEXT WEEK FOCUS & KEY ACTIONS | [6 empty] | STAKEHOLDERS — FOCUS REQUIRED
1. Close design approval – escalate by Jul 12 | [6 empty] | Client: Approve design by Jul 12 (Blocks Dev start → ~1 wk delay)
2. Start Dev Sprint 2 – unblock immediately after sign-off | [6 empty] | Sponsor: Approve budget increase (+$1.5K) by Jul 15
3. Resolve vendor API dependency – enforce SLA | [6 empty] | Vendor: Confirm API readiness & SLA by Jul 18 (QA delays 3–5 days)
4. Sponsor decision on budget overrun by Jul 15 | [6 empty] | PM: Drive escalation + daily tracking until design/API closure

## _Lists (hidden)
RAG | MS_STATUS | HM_STATUS | RISK_TYPE | OWNER | PHASE | SPRINT | DEC_RAG | DEP_RAG | WEEK | IMPACT
🟢 GREEN | ✔️ On Track | 🔴 CRITICAL | 🔴 Risk | PM | Planning | Sprint 1 | 🔴 Critical | 🔴 Critical | 1 | 🔴 High
🟠 AMBER | ⚠️ Delayed | 🟠 AT RISK | 🟠 Issue | Tech Lead | Development | Sprint 2 | 🟠 Amber | 🟠 At Risk | 2 | 🟠 Medium
🔴 RED | 📅 Upcoming | 🟢 ON TRACK | 🟡 Assumption | Sponsor | Testing | Sprint 3 | ⚫ Monitoring | 🟢 On Track | 3 | 🟢 Low
| 🔴 Critical |  | 🔵 Dependency | Client | UAT | Sprint 4 |  |  | 4
| ✅ Complete |  |  | Vendor | Go Live | Sprint 5 |  |  | 5
| 🟠 At Risk |  |  | HR | Closure | Sprint 6 |  |  | 6
|  |  |  | Design Lead |  |  |  |  | 7
|  |  |  | Product Owner |  |  |  |  | 8
|  |  |  | Steering Committee |  |  |  |  | 9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52