PROJECT CHARTER Digital Platform Upgrade ¦ Execution-Ready

PM: Latha Lakshmanan ¦ Sponsor: Program Director / CFO ¦ Report Date: 19-Apr-2026 ¦ Status: AMBER - Action Required

| 01 PROJECT SNAPSHOT |  |  |  |
| --- | --- | --- | --- |
| Project Name | Digital Platform Upgrade | Sponsor | Program Director / CFO |
| Project Manager | Latha Lakshmanan | Client | Internal / Enterprise |
| Start Date | January 2026 | Target Go-Live | August 15, 2026 |
| Current Phase | Development - Sprint 4 / Week 12 | Report Date | 19-Apr-2026 |
| Overall Status | AMBER - Action Required | Progress | 65% Complete |
| Budget | $10,000 approved ¦ EAC $11,500 (↑$1,500) | One-Line Summary | Slight delay: design dependency + client & sponsor decisions required urgently |
| Rule: Document this before any stakeholder meeting. Ambiguity here causes every downstream conflict. |  |  |  |

| 02 OBJECTIVES & SUCCESS CRITERIA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Metric | Target | Owner | Date | Business Outcome |
| Deliver fully functional platform | UAT pass rate | 100% - 0 P1 defects | PM / QA Lead | Aug 15 | Market-ready platform enabling new revenue streams |
| Go-live by August 15, 2026 | Production deployment | On / before Aug 15 | PM | Aug 15 | Revenue realization on schedule; contract milestone achieved |
| Deliver within approved budget | Cost variance | ≤ +15% sponsor-approved | Finance / PM | Aug 15 | Financial discipline; no unplanned capital draw |
| Vendor API integration complete | Integration test pass | 100% test cases pass | Tech Lead | Jul 25 | Single vendor dependency resolved; QA phase unblocked |
| Reduce processing time (post-delivery) | Avg end-to-end cycle time | -30% vs baseline | Ops Lead | Oct 2026 | Cost reduction + faster revenue cycle (primary business value) |
| Rule: If these metrics are not met at the stated dates, the project is NOT considered successful - even if delivered. |  |  |  |  |  |

| 03 SCOPE DEFINITION - CONTROL BOUNDARY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Category | Item | Detail | Owner | Validation Method | Backlog Ref |
| IN SCOPE | Platform design & development | UI/UX, backend, database - per backlog v1.2 | PM | Client design sign-off | BL-v1.2 #001–028 |
| IN SCOPE | Vendor API integration | Single vendor only; per SLA confirmed by Jul 18 | Tech Lead | Integration test pass | BL-v1.2 #034–041 |
| IN SCOPE | QA & User Acceptance Testing | Functional + integration testing; UAT by client | QA Lead | 0 Sev1 defects + client sign-off | BL-v1.2 #055–062 |
| IN SCOPE | Production deployment | Go-live Aug 15; rollback plan tested and ready | PM | Sponsor go/no-go sign-off | BL-v1.2 #070 |
| OUT OF SCOPE | Mobile application rebuilds | Deferred to Phase 2 - not approved this cycle | Product | N/A - future CR required | — |
| OUT OF SCOPE | Third-party integrations (beyond named vendor) | Any system not in backlog v1.2 | PM | N/A | — |
| OUT OF SCOPE | Post go-live maintenance & support | Ops team responsibility from Aug 16 onwards | Ops | Ops handover document | — |
| OUT OF SCOPE | End-user training program | Separate project; separate budget | L&D | N/A | — |
| Rule: Anything not listed as IN SCOPE is OUT OF SCOPE. All additions require a formal Change Request. |  |  |  |  |  |

| 03A SCOPE BASELINE - SIGN-OFF BLOCK |  |  |  |
| --- | --- | --- | --- |
| Backlog document | Product Backlog v1.2 - SharePoint: /DPU-2026/Backlog/Backlog_v1.2_15Mar2026.xlsx | Scope version | Scope v1.0 - locked 19-Apr-2026. Any change after this date requires a formal CR. |
| Sponsor - Scope confirmed | Name: ________________________________________ Signature: ________________________________________ Date: ________________________________________ | Client - Scope confirmed | Name: ________________________________________ Signature: ________________________________________ Date: ________________________________________ |
| Rule: Scope v1.0 signed on the dates above is the baseline. Anything not IN SCOPE is OUT. No verbal additions accepted. All changes require a formal Change Request. |  |  |  |

| 04 MILESTONES & TIMELINE BASELINE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Milestone | Date | Owner | Status | Exit Criteria (Definition of Done) |
| Design Sign-off | Jul 12 (revised) | Client / Design Lead | DELAYED | Approved design baseline signed; zero open design comments; PM notified in writing |
| Development Sprint Complete | Jul 25 | Dev Lead / PM | ON TRACK | All sprint 4 stories done; code reviewed; merged to staging; demo approved |
| QA & Testing | Aug 5 | QA Lead | UPCOMING | 100% test cases executed; zero Sev1/Sev2 defects open; signed QA report issued |
| Go-Live / Production | Aug 15 | PM / Sponsor | UPCOMING | Production deployment complete; rollback tested; sponsor go/no-go approval obtained |
| Rule: A milestone is not complete without its Exit Criteria satisfied in writing. Dates alone are not completion. |  |  |  |  |

| 05 BUDGET CONTROL |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Amount | Owner | Status | Notes |
| Base Budget (Approved) | $10,000 | Sponsor | APPROVED | Baseline locked at kick-off. No changes without formal CR. |
| Spent to Date | $6,000 (60%) | PM | ON TRACK | 60% consumed at 65% completion - within expected burn rate. |
| Forecast at Completion (EAC) | $11,500 | Finance / PM | AT RISK | Variance +$1,500 over baseline. Sponsor approval required by Jul 15. |
| Contingency Reserve | $1,000 | PM (controlled) | AVAILABLE | For known risks only. PM can draw without sponsor approval. |
| Management Reserve | $2,000 | Sponsor (controlled) | UNTOUCHED | For unknown unknowns only. Sponsor approval required to access. |
| Current Variance | + $1,500 over approved | Sponsor | ACTION REQUIRED | Scope review in progress. Non-essentials being deferred to v2. |
| Rule: Contingency = known risks (PM controls). Reserve = unknowns (Sponsor controls). NOT interchangeable. |  |  |  |  |

| 06A RISK APPETITE STATEMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Risk Category | Appetite Level | Tolerance Threshold | Escalation Trigger | Sponsor Statement |
| Schedule / timeline | LOW | Delay > 5 days on any milestone | Any milestone slippage triggers immediate PM → Sponsor escalation | We cannot accept go-live beyond Aug 15 without executive re-authorisation. |
| Budget | LOW–MEDIUM | Variance > 5% of approved base | Any EAC increase beyond approved budget requires sponsor decision within 48 hrs | Current +$1,500 variance is at threshold. No further overrun accepted without scope cut. |
| Scope | VERY LOW | Any addition outside signed scope v1.0 | All scope changes blocked pending formal CR and sponsor approval | Zero tolerance for scope creep. All additions must be formally approved and funded. |
| Security / data | ZERO | Any confirmed data breach or Critical vulnerability open at go-live | Immediate project pause; PM + CISO + Sponsor notified within 1 hour | Zero tolerance. No go-live with open Critical security issues under any circumstances. |
| Vendor dependency | MEDIUM | Vendor API delivery delayed > 3 days beyond Jul 18 | PM + Tech Lead to trigger contingency plan; sponsor notified same day | Vendor delay is manageable IF parallel dev track is maintained. Beyond 5 days: go-live risk. |

| 06B RAID REGISTER - SEED (Risks, Assumptions, Issues, Dependencies) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk ID | Type | Description | Owner | Due | Prob | Impact | Mitigation | If Unresolved |
| R-001 | RISK | Late client design sign-off pending | PM | Jul 12 | H | H | Escalate with sponsor backing; enforce hard deadline | Blocks Dev Sprint; cascades to go-live |
| R-002 | RISK | Budget overrun forecast +$1,500 | Sponsor | Jul 15 | M | H | Scope review; defer non-essentials to v2 | Sponsor approval needed; possible scope cut |
| R-003 | RISK | DPIA not started — due Jun 30 | PM + Legal | Jun 1 | H | H | Initiate immediately with Legal; escalate if no Legal resource by Jun 1 | Legal / compliance breach; go-live blocked |
| I-001 | ISSUE | Vendor API not ready; SLA unconfirmed | Tech Lead | Jul 18 | - | H | Daily vendor follow-up; parallel dev where possible | QA delayed 3–5 days; go-live at risk |
| A-001 | ASSUMPTION | Vendor confirms API SLA by Jul 18 | Tech Lead | Jul 15 | - | H | Weekly validation; escalation if unconfirmed | Becomes critical blocker if invalidated |
| A-002 | ASSUMPTION | Client approves design sign-off by Jul 12 | PM | Jul 10 | - | H | Daily follow-up; PM escalates to sponsor if needed | Design delay cascades entire schedule |
| D-001 | DEPENDENCY | Design sign-off (hard gate) — Client | Client | Jul 12 | - | H | Escalate if client unavailable; sponsor to intervene | Entire Dev Sprint blocked |
| D-002 | DEPENDENCY | Sponsor budget approval (+$1,500) | Sponsor | Jul 15 | - | H | Impact analysis presented; clear approve/reject request | Scope cut or resource slowdown |
| Rule: Unvalidated assumptions become risks after their due date. Reference by ID in all steering meetings. R-003 (DPIA) requires immediate action. Score = Probability × Impact. Fix H×H items first. |  |  |  |  |  |  |  |  |

| 07 STAKEHOLDER MAP - POWER, NOT TITLES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stakeholder | Influence | Behavior | Risk Level | Primary Interest / Agenda | Engagement Strategy |
| Sponsor (CFO) | HIGH | Decisive | MEDIUM | Cost control; delivery within budget | Weekly steering; data-driven updates; 48-hr decision SLA enforced |
| Client / Design Lead | HIGH | Demanding | HIGH | Feature quality; specific expectations | Daily follow-up; named deadlines; escalation if no response by Jul 10 |
| Latha Lakshmanan (PM) | HIGH | Proactive | LOW | Delivery success; team performance | Full ownership; all-channel daily tracking; RAID log management |
| Tech Lead | MEDIUM | Analytical | MEDIUM | Technical quality; vendor reliability | Sprint stand-ups; RAID ownership; vendor SLA enforcement |
| Vendor | MEDIUM | Variable | HIGH | Timely payment; clear SLA terms | Weekly SLA check-in; formal SLA doc; escalation trigger if delayed |
| QA Lead | MEDIUM | Methodical | LOW | Clean test environment; zero defects | Sprint reports; defect log; involved from design sign-off stage |
| Rule: Unengaged high-influence stakeholders are a top project risk. Engage by agenda, not seniority. |  |  |  |  |  |

| 08 DECISION RIGHTS & PM AUTHORITY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Decision Type | PM Authority | Threshold | Sponsor Required | Notes / Enforcement |
| Budget reallocation | YES - unilateral | Within ±5% of approved baseline | NO | PM documents decision; notifies Sponsor within 24 hrs |
| Budget increase (over threshold) | NO - escalate immediately | Any increase > 5% | YES - within 48 hrs | Project paused if no decision after 72 hrs |
| Scope addition or removal | NO - CR required | Any scope item | YES - formal CR approval | Change Request process mandated; no verbal approvals |
| Timeline shift - minor | YES - unilateral | ≤ 10 days; no milestone impact | NO | PM updates plan; notifies all stakeholders same day |
| Milestone date change | NO - sponsor decision | Any milestone date shift | YES | Full impact assessment + stakeholder communication triggered |
| Vendor / contract decisions | NO - sponsor required | Any contract amendment | YES | PM manages operations only; Sponsor signs contract changes |
| Risk response (within RAID plan) | YES - unilateral | All RAID-logged risks | NO | PM executes approved mitigations; reports in weekly status |
| Rule: PM has full authority within defined thresholds. No re-approval needed within limits. Escalation: PM → Sponsor (24 hrs) → Exec (48 hrs). |  |  |  |  |

| 09 CHANGE CONTROL - NO EXCEPTIONS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Step | Action | Owner | SLA | Enforcement Rule |
| 1 - Log Request | Stakeholder raises formal Change Request (CR) with unique ID. Verbal requests are NOT accepted under any circumstances. | Any stakeholder | Same day | No CR ID = request does not exist. PM will not act on undocumented requests. |
| 2 - Impact Assessment | PM assesses impact on scope, schedule, cost, quality, and RAID. Documents findings formally. | PM | Within 48 hrs | Assessment is mandatory before any approval discussion begins. |
| 3 - Sponsor Review | PM presents impact assessment + recommendation with a clear, time-bounded decision request. | PM + Sponsor | Within 48 hrs of assessment | Sponsor must respond within 48 hrs. non-response = escalation trigger. |
| 4 - Decision & Baseline Update | Sponsor approves or rejects. Approved CRs update project baseline immediately. Baseline is the new contract. | Sponsor | Decision within 3 business days | Once approved, baseline is final. No further renegotiation of the same item. |
| 5 - Communicate & execute | PM notifies all impacted stakeholders. Team executes only after written approval is confirmed. | PM + Team | Within 1 business day of decision | Work without approved CR is unauthorized and may be reversed by PM. |
| Rule: Work executed without an approved Change Request is unauthorized. No verbal approvals recognized. No exceptions. |  |  |  |  |

| 10 COMMUNICATION & ESCALATION PLANS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Communication | Audience | Frequency | Format | Owner | Content / Output Definition |
| Weekly Status Report | All stakeholders + Sponsor | Every Monday | Email + PDF | PM | RAG status, top 3 risks, decisions needed, variance vs baseline |
| Sprint Stand-up | Dev + QA Team | Daily (15 min) | Teams / verbal | Tech Lead | Blockers, progress, dependencies - no status theatre |
| Steering Committee Review | Sponsor + PM + Client | Weekly | Meeting + slide | PM | Milestone status, budget update, decisions required with hard deadlines |
| Escalation - Critical Alert | Sponsor | Within 24 hrs of RED | Direct call + email | PM | Issue, impact, options, recommended action, decision deadline stated |
| Stakeholder Decision Request | Client / Sponsor / Vendor | On-demand (with deadline) | Email + decision log | PM | Specific question, response deadline, impact of non-response clearly stated |
| RAID Log Update | PM + Tech Lead | Weekly | Shared register | PM | All items: current status, owner, next action, trigger date |
| Rule: RED status → Sponsor notified within 24 hrs. Decision SLA (Sponsor): 48 hrs. non-response escalated to Executive Committee. |  |  |  |  |  |

| 11 EXTERNAL DEPENDENCIES - EXPLICIT CONTRACTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Dependency | Owner | Due Date | Impact if Missed | Mitigation / Contingency |
| Design sign-off (hard gate) | Client / Design Lead | Jul 12 (revised from Jul 10) | Blocks entire Dev Sprint; 1-week+ cascade delay to go-live | PM escalates to Sponsor if client unavailable; daily follow-up from Jul 9 |
| Vendor API readiness + SLA confirmation | Vendor | Jul 18 | Delays QA phase 3–5 days; go-live at risk | Parallel development where possible; formal SLA trigger by PM + Tech Lead |
| Sponsor budget approval (+$1,500 variance) | Sponsor | Jul 15 | Scope reduction enforced; resource slowdown; team impact | PM presents formal impact analysis; clear approve/reject decision request issued |
| Client UAT sign-off | Client | Aug 10 | Go-live delayed; production deployment blocked | UAT entry criteria defined from Aug 5; QA lead coordinates environment |
| Rule: Each dependency has a named owner and a hard due date. Missed dependencies are escalated to Sponsor within 24 hrs. |  |  |  |  |

| 12A ROLES & ACCOUNTABILITY - RACI (CRITICAL DELIVERABLES) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Deliverable | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed) | Notes |
| Platform design (approved baseline) | Dev Lead + Designer | PM | Architect + Client | Sponsor | Client sign-off is the gate. No development begins without it. |
| Vendor API integration | Tech Lead | PM | Dev Team | Client + Vendor | SLA must be written and signed before integration work begins. |
| QA test execution | QA Lead | PM | Dev Lead | Client | Entry criteria: design signed off. Exit: 0 Sev1 defects + signed report. |
| User Acceptance Testing (UAT) sign-off | Client | Client | QA Lead + PM | Sponsor | Client owns UAT. PM provides environment and coordination support only. |
| Production deployment | Dev Lead | PM | Ops + Tech Lead | All stakeholders | Rollback plan must be tested and approved before go-live window opens. |
| Benefits review (post-delivery) | Ops Lead | Sponsor | Finance + PM | Executive | Mandatory 30-day and 90-day checkpoints. Sponsor accountable. No exceptions. |
| Rule: If no A (Accountable) is assigned, PM assumes accountability by default. There must be exactly ONE A per deliverable. |  |  |  |  |  |

| 12B RESOURCE ALLOCATION & BACKUP CONTACTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Role / Person | Deliverable Focus | Allocation % | Sprint 4 Days/Wk. | Backup Person | Backup Availability |
| Latha Lakshmanan (PM) | Full project management; escalation; comms | 100% | 5 days | [Deputy PM / Programme Manager] | Available within 4 hrs — notify Sponsor if PM unavailable > 1 day |
| Dev Lead | Platform build; sprint delivery; staging | 80% | 4 days | [Senior Developer — name TBD] | Can cover sprint planning; PM to re-scope if > 3 days |
| Tech Lead | Vendor API; architecture; technical decisions | 70% | 3.5 days | Dev Lead (partial cover) | Architecture decisions: escalate to CTO if Tech Lead unavailable > 2 days |
| QA Lead | Test planning; execution; defect management | 50% | 2.5 days | [QA Analyst — name TBD] | Can execute; sign-off authority remains with QA Lead only |
| Designer | UI/UX design; client sign-off support | 40% | 2 days | PM (coordination only) | Design decisions: client must re-engage; PM cannot substitute |
| Client / Design Lead | Design approval; UAT; business decisions | On-demand | As needed | [Business Analyst or Deputy] | All sign-off authority remains with Client only — no substitution for sign-off |
| Rule: If no A (Accountable) is assigned, PM assumes accountability by default. Exactly ONE A per deliverable. Backup contacts must be confirmed before sprint 5. |  |  |  |  |  |

| 13 BENEFITS REALIZATION - POST-DELIVERY OWNERSHIP |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Benefit | Metric | Target | Owner | Review Date | Validation Method |
| Processing efficiency gain | Avg end-to-end cycle time | -30% vs pre-go-live baseline | Ops Lead | Oct 2026 (+30 days) | Time-motion study; before-and-after measurement report |
| Operational cost reduction | Monthly operating cost | -15% reduction | Finance | Nov 2026 (+90 days) | Finance monthly P&L report vs pre-project baseline |
| Platform uptime / reliability | System uptime SLA | ≥ 99.5% monthly | Ops | Sep 2026 onwards | Automated monitoring dashboard; monthly ops report |
| User adoption rate | Active user’s vs intended users | ≥ 80% within 90 days | Product / Ops | Nov 2026 | Usage analytics; user activation tracking report |
| Revenue enablement | Revenue attributable to platform | Baseline TBD by Sponsor | CFO / Sponsor | Dec 2026 | Finance attribution model; quarterly revenue review |
| Rule: Project is only successful if benefits are realized - not just delivered. Sponsor is accountable for all review checkpoints. |  |  |  |  |  |

| 14 SPONSOR COMMITMENT - EXPLICIT OBLIGATIONS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Commitment | Target SLA | Owner | Consequence if Missed | Logged As (RAID) |
| Decision turnaround on any request | 48 hours maximum | Sponsor | Escalated to Executive Committee; project timeline impacted | Risk R-001 |
| Steering committee participation | Weekly (every Monday) | Sponsor | Decisions deferred; blockers unresolved; team morale impacted | Risk R-002 |
| Escalation availability (RED items) | 24 hours response | Sponsor | PM escalates to Executive Committee unilaterally | Risk R-003 |
| Budget decision - EAC approval (+$1,500) | By Jul 15, 2026 | Sponsor | Scope reduction enforced; resource slowdown mandated | Decision D-002 |
| Benefits realization review | 30-day + 90-day post go-live | Sponsor | Benefits unverified; ROI assumptions invalid; audit risk | Dependency DEP-005 |
| Rule: Sponsor unavailability is a RAID-logged project risk. It does NOT suspend project timelines or PM authority. |  |  |  |  |

| 15 PROJECT CLOSURE CRITERIA |  |  |  |  |
| --- | --- | --- | --- | --- |
| Closure Element | Criteria / Requirement | Owner | Target Date | Action if Not Met |
| Formal go-live sign-off | Production deployment complete; sponsor go/no-go issued in writing; rollback plan tested and on standby | PM + Sponsor | Aug 15, 2026 | Go-live postponed; sponsor re-authorises new date via CR |
| UAT completion sign-off | Client confirms in writing: all UAT test cases passed, 0 Sev1 defects open, platform accepted for production | Client / QA Lead5 | Aug 10, 2026 | UAT extended; go-live blocked until written acceptance received |
| Outstanding defects cleared | All Critical and High defects remediated and retested. Medium defects: documented, owner assigned, post-go-live backlog created | QA Lead | Aug 13, 2026 | Go-live blocked for Critical. Medium: documented waiver signed by Sponsor required |
| Vendor SLA confirmed in writing | Vendor API SLA signed document received; performance baseline agreed and logged | Tech Lead | Jul 18, 2026 | Integration phase paused; vendor escalated; Sponsor notified |
| Handover to operations | Ops team briefed; runbook delivered; monitoring dashboards live; on-call escalation path agreed | PM + Ops | Aug 15, 2026 | Go-live blocked until ops team confirms readiness in writing |
| Benefits baseline captured | Pre-go-live metrics recorded (cycle time, cost, uptime) to enable post-delivery comparison at 30 and 90 days | Ops Lead | Aug 14, 2026 (day before go-live) | Benefits realization measurement impossible; Sponsor to accept risk in writing |
| Project formally closed | PM issues Project Closure Report; RAID log archived; all documents moved to /Archive/; team released from project | PM | Aug 22, 2026 (+1 week post go-live) | PM to notify Sponsor of delay; no team resource released until closure confirmed |
| Post-project audit (if triggered) | If cost variance > 10% OR go-live delayed > 2 weeks: mandatory lessons-learned report within 30 days | PM + Sponsor | Sep 15, 2026 | Audit report late: PM accountable; Sponsor informed; report shared with Executive Committee |
| Rule: Project is not closed until the PM issues a written Project Closure Report accepted by the Sponsor. 'Done' is not closure. |  |  |  |  |

| 16 DELIVERY OPERATING MODEL |  |  |  |  |
| --- | --- | --- | --- | --- |
| Element | Approach | Cadence | Owner | Notes / Kill Criteria |
| Methodology | Hybrid Agile - sprints within waterfall milestone gates | Sprint-level planning | PM | Agile delivery inside fixed gates (design sign-off, go-live). Both discipline and flexibility required. |
| Sprint Cycle | 2-week sprints with backlog prioritization | Every 2 weeks | Dev Lead | Sprint 4 active. Sprint retros mandatory. No undefined stories enter a sprint. |
| Governance Rhythm | Steering committee + weekly status report | Weekly (Mondays) | PM | Decisions logged; actions tracked in RAID. No governance = no cover for the PM. |
| Definition of Ready | Story has AC, design reference, and effort estimate | Before each sprint start | PM + Dev Lead | No story enters a sprint without being fully defined. PM enforces this gate. |
| Definition of Done | Code reviewed, tested, merged, documented, demo-ready | End of each sprint | QA Lead | Incomplete stories return to backlog. Nothing is 'done' informally. |
| Kill Criteria | Pause if: delay > 4 weeks OR cost variance > 30% OR critical dependency fails with no alternative | Rolling - every steering review | Sponsor | Protects against sunk-cost decisions. Sponsor decides within 48 hrs.: proceed / pause / terminate. |
| Rule: Kill criteria protect the organization from sunk-cost decisions. Sponsor decides within 48 hrs of threshold breach. |  |  |  |  |

| 17A VERSION HISTORY & CHANGE LOG |  |  |  |  |
| --- | --- | --- | --- | --- |
| Version | Date | Author | Approved By | Change Summary |
| v0.1 | 10-Jan-2026 | Latha Lakshmanan | Sponsor (draft review) | Initial draft — project concept and scope outline |
| v0.2 | 01-Feb-2026 | Latha Lakshmanan | Sponsor | Budget baseline and milestone schedule added |
| v0.3 | 15-Mar-2026 | Latha Lakshmanan | Sponsor + Client | RAID seed register, stakeholder map, RACI added |
| v1.0 | 19-Apr-2026 | Latha Lakshmanan | Sponsor + Client + PM | Full charter — all 18 sections complete; formally signed and distributed |
| v1.1 | Apr-2026 | Latha Lakshmanan | Sponsor | CORRECTED: Business case, scope sign-off, risk IDs, risk appetite, RACI resource %, backup contacts, closure criteria, security classification, numbering — all gaps from audit fixed |

| 17B DOCUMENT ACCESS, AUTHORITY & DISTRIBUTION |  |  |  |  |
| --- | --- | --- | --- | --- |
| Stakeholder / Role | Access Level | Can Edit Charter? | Distribution Method | Notes |
| Sponsor (CFO) | FULL READ + APPROVE | YES — formal versions only | Email (PDF) + SharePoint | Receives every version. Signs off on all major versions (v1.0+). |
| Project Manager (Latha) | FULL READ + EDIT | YES — all versions | SharePoint (edit access) | Charter owner and sole editor. Responsible for version control. |
| Client / Design Lead | READ ONLY | NO | Email (PDF) — signed versions only | Receives approved versions only. Changes via Change Request process. |
| Tech Lead | READ ONLY — Sections 3,6,8,11,12 only | NO | SharePoint (view link) | Access limited to relevant sections. No financial or stakeholder data. |
| QA Lead | READ ONLY — Sections 4,6,12 only | NO | SharePoint (view link) | Receives milestone, RAID, and RACI sections only. |
| Vendor | READ ONLY — Sections 3, 11 only | NO | Email (PDF extract — named sections only) | No financial data. No stakeholder map. Scope and dependency sections only. |
| External Auditor | READ ONLY — Full document | NO | Secure share (auditor portal) | Full access only upon formal audit request with written sponsor authorization. |

| 17C DOCUMENT STORAGE, RETENTION & CONTROL RULES |  |  |  |
| --- | --- | --- | --- |
| Control Element | Requirement | Owner | Consequence if breached |
| Master document location | SharePoint: /Projects/DPU-2026/Charter/ — single source of truth. No email copies are authoritative. | PM | Unauthorized copies invalidated; PM tracks and removes |
| File naming convention | PROJECT_CHARTER_DPU_v[X.X]_[YYYYMMDD].docx — strictly enforced | PM | Non-compliant document treated as invalid |
| Version approval requirement | Every version ≥ v1.0 requires sponsor signature before distribution | PM + Sponsor | Distribution of unsigned version = policy breach |
| Retention period | 7 years post project closure (regulatory / internal audit requirement) | PM + IT / Records | Premature deletion = compliance risk. PM personally accountable. |
| Change trigger for new version | Any approved CR modifying scope, budget, or milestones triggers a new charter version within 2 business days | PM | Outdated charter used for decisions = governance failure. RAID risk logged. |
| Superseded version handling | Archived in /Archive/; watermarked SUPERSEDED; original metadata preserved | PM | Active use of superseded version = misalignment risk. PM to issue correction. |
| Rule: The charter is a controlled document. Only the PM may edit it. All stakeholders receive read-only access. Unauthorized edits are invalid. |  |  |  |

| 18A INFORMATION SECURITY CLASSIFICATION |  |  |  |
| --- | --- | --- | --- |
| Section / Data Type | Classification Level | Handling Requirement | Rationale |
| Full Project Charter (all sections) | CONFIDENTIAL - INTERNAL | Encrypted storage; named distribution only; no public sharing | Contains budget, vendor SLA terms, and executive decision data |
| Business Case & ROI Data (Section 00) | RESTRICTED | Sponsor + PM + CFO + Finance only; never shared externally | Strategic and financial data — commercially sensitive; not for vendor or client |
| Budget & Financial Data (Section 05) | RESTRICTED | Sponsor + PM + Finance only; never shared externally | EAC, variance, and reserve data — commercially sensitive |
| Vendor SLA Terms (Section 11) | RESTRICTED | PM + Tech Lead + Sponsor only; redacted version for vendor | Commercial contract terms; confidentiality clause applies |
| RAID Register (Section 06) | CONFIDENTIAL - INTERNAL | Project team + Sponsor; not distributed to vendor or client in full | Risk exposure data could be used adversely in commercial negotiations |
| Scope Definition (Section 03) | INTERNAL | Full team; vendor receives IN/OUT scope only — no validation methods | Scope boundary is operational; vendor does not need internal validation criteria |
| Stakeholder Map (Section 07) | RESTRICTED | PM + Sponsor only; never shared externally | Influence ratings and behavioral profiles are internal assessments |
| Milestone & Status Data (Sections 04, 10) | INTERNAL | Full project team + Sponsor; client receives summary only | Full delay analysis must not be shared without PM review first |

| 18B SECURITY REVIEW GATES & APPROVAL REQUIREMENTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Review Gate | Trigger | Reviewer | SLA | Approval Requirement & Outcome |
| Initial security assessment | At project kick-off — before development begins | InfoSec Lead + PM | Within 5 business days of kick-off | Formal sign-off required from InfoSec Lead before Sprint 1 commences |
| Vendor security review | Before vendor API integration (before Jul 18) | InfoSec Lead + Tech Lead | Within 3 business days of SLA confirmation | Vendor must pass security questionnaire; API must use OAuth 2.0 auth protocol |
| Data classification review | When scope or data handling changes | InfoSec Lead + PM | Within 2 business days of change | Updated classification table submitted to Sponsor; no new data type used without approval |
| Pre-production security scan | Before go-live deployment (Aug 12–13) | InfoSec Lead + QA Lead | Completed by Aug 13 (2 days pre-go-live) | Zero Critical/High vulnerabilities at go-live. Medium: documented + owner assigned. |
| Penetration test (if applicable) | If platform handles PII or financial transactions | External pen tester (approved vendor) | 4-week lead time; planned by Jul 1 | Go/no-go gate for go-live. All Critical findings remediated before production. |
| Post go-live security audit | 30 days after go-live (Sep 15, 2026) | InfoSec Lead | Within 30 days of Aug 15 | Audit report issued to Sponsor. Open findings logged in RAID. Next: 90 days. |

| 18C SECURITY SLA COMMITMENTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| SLA Type | Threshold | Owner | Breach Consequence | Measurement Method |
| Security incident - CRITICAL | Acknowledged: 1 hr. Contained: 4 hrs. | InfoSec Lead + PM | Project paused; Sponsor + CISO notified immediately | Automated SIEM alerting; PM logs in RAID within 1 hr |
| Security incident - HIGH | Acknowledged: 4 hrs. Contained: 24 hrs. | InfoSec Lead + Tech Lead | PM notified; risk assessment within 4 hrs; RAID updated | InfoSec incident log; PM weekly status updated |
| Security incident - MEDIUM / LOW | Acknowledged: 1 business day. Remediated: 5 business days. | Tech Lead | Logged in RAID; reviewed at next steering meeting | RAID register; sprint backlog item created |
| Vulnerability - CRITICAL | Remediated before next production deployment; no exceptions | Tech Lead + Dev Lead | Go-live blocked until resolved; Sponsor informed | Pre-deployment scan report; QA sign-off required |
| Vulnerability - HIGH | Remediated within 5 business days of discovery | Tech Lead | P1 sprint backlog; PM escalates if unresolved at day 5 | Vulnerability tracker; sprint board |
| Data breach notification (regulatory) | Regulator notified within 72 hrs of confirmed breach (GDPR) | PM + CISO + Legal | Legal/regulatory consequences; project suspension possible | Legal counsel engaged; mandatory reporting timeline tracked |
| Third-party vendor security assessment | Completed before vendor API goes live (due Jul 16) | InfoSec Lead | Vendor API access blocked; go-live delayed | InfoSec assessment scorecard; PM approval required to proceed |

| 18D DATA PRIVACY, COMPLIANCE & REGULATORY REQUIREMENTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Requirement | Applicable Regulation | Owner | Due / Review Date | Status & Action Required |
| Data Privacy Impact Assessment (DPIA) | GDPR / Local Data Protection Law | PM + Legal | Complete by Jun 30, 2026 | NOT STARTED — PM to initiate with Legal by Jun 1 |
| Data minimization review | GDPR Article 5 / Privacy by Design | Tech Lead + InfoSec | Before sprint 2 data design finalized | Tech Lead to confirm only necessary data fields are collected and stored |
| Consent management mechanism | GDPR Article 6 / Applicable regulation | Tech Lead + PM | Built into platform by development sprint | Consent flow must be reviewed by Legal before UAT begins — hard gate |
| Data retention & deletion policy | GDPR Article 17 / Records Management Policy | Ops + Legal | Defined before go-live; built into platform | Automated deletion triggers required; manual process not acceptable at scale |
| Third-party data sharing agreement (DPA) | GDPR Article 28 / Vendor contracts | Legal + PM | Before vendor API integration (before Jul 12) | DPA with vendor required before any data flows — go-live blocker if missing |
| Regulatory sign-off | Sector-specific regulation (confirmed by Legal) | Legal + Sponsor | Before go-live — Aug 10 latest | Legal to confirm regulatory clearance. Go-live is BLOCKED without written sign-off. |
| Rule: No system goes live without InfoSec sign-off. Security SLA breaches are RAID risks. Data privacy obligations are legally binding - not optional. |  |  |  |  |

| 19 FORMAL AUTHORIZATION - SIGN-OFF |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name | Role | Commitments by Signing | Date | Signature |
| [Program Director / CFO] | Sponsor | Authorizes charter v1.1; approves budget & scope changes within 48 hrs; commits to weekly steering, 24-hr escalation availability, and benefits review at 30 and 90 days post go-live |  |  |
| Latha Lakshmanan | Project Manager | Accepts PM authority within defined limits; commits to weekly reporting, RAID management, change control enforcement, and issuance of Project Closure Report |  |  |
| [Client / Design Lead] | Business Client | Commits to scope sign-off (Sec 03A) by agreed date; design sign-off by Jul 12; UAT participation; timely decisions per charter deadlines; UAT sign-off by Aug 10 |  |  |
| [InfoSec Lead] | Information Security | Confirms security review schedule (Sec 18B); commits to pre-go-live scan completion by Aug 13; post go-live audit by Sep 15 | ___________ | ________________ |
| Rule: By signing, all parties confirm they have read and agree to: scope boundaries, decision authority, change control, resource commitments, and security obligations. |  |  |  |  |