## 📋 Instructions
RACI RESPONSIBILITY ASSIGNMENT MATRIX ¦ Project Governance Tool
Version 1.0 ¦ Last Updated: [Date] ¦ Project: [Project Name] ¦ Status: [ACTIVE]
🎯 PURPOSE OF THIS TEMPLATE
Why RACI? | Unclear roles cause 40-60% of project delays. This template defines WHO does WHAT, WHO decides, WHO advises, and WHO needs updates — eliminating ambiguity before it derails your project.
When to build it? | During project INITIATION — before sprint planning, resource allocation, or vendor kick-off. Review at every phase gate and whenever team members change.
Golden Rule | Every task must have ✅ exactly ONE Accountable (A). Multiple A's = nobody is accountable. Zero A's = no owner. The Health Check tab flags both automatically.
📌 RACI DEFINITIONS & USAGE RULES
R | RESPONSIBLE — The person or team who performs the actual work. There can be multiple R's.
▸ Rule: At least ONE R per task. Tag individuals, not just departments.
A | ACCOUNTABLE — The single owner who approves the outcome and answers for it. The 'buck stops here' role.
▸ Rule: ⚠️ EXACTLY ONE per task — never zero, never two. Usually a senior role.
C | CONSULTED — Subject matter experts who provide input BEFORE a decision is made. Two-way dialogue.
▸ Rule: Use sparingly. Too many C's slow decisions. Limit to true SMEs with relevant expertise.
I | INFORMED — Stakeholders who receive updates AFTER decisions/milestones. One-way communication.
▸ Rule: Prefer I over C when input is not needed. Over-consulting inflates meeting load.
🗂️ WORKBOOK STRUCTURE — 5 SHEETS
📋 Instructions | This sheet. Read before use.
🎯 RACI Matrix | MAIN WORKING SHEET. Enter R / A / C / I for each task × stakeholder cell. Use the dropdown.
👥 Stakeholders | Register all project stakeholders: name, role, department, email. Feed names into the matrix.
📊 Health Check | Auto-calculated dashboard. Flags missing A, duplicate A, over-consulted roles, orphan tasks.
📝 Change Log | Record every RACI change: who changed what, when, and why. Audit trail for governance.
🚨 COMMON RACI FAILURES & HOW THIS TEMPLATE PREVENTS THEM
FAILURE | HOW THIS TEMPLATE ADDRESSES IT
⚠ Multiple owners = no owner | ✅ Health Check flags any task with more than one A in red. One A only, enforced visually.
⚠ 'IT will handle it' ambiguity | ✅ Stakeholder sheet maps individuals — no department-level assignments allowed.
⚠ Vendor accountability gaps | ✅ Vendor rows included in stakeholder register. Vendor PM must hold A or R on delivery tasks.
⚠ Sponsor not looped in | ✅ Sponsor column pre-built. Health Check warns if Sponsor has zero I assignments.
⚠ RACI not updated after change | ✅ Change Log tab records every update. Version + date tracked in cell B5 of each sheet.
⚠ QA/UAT ownership confusion | ✅ Dedicated phase rows for QA sign-off, UAT approval with explicit A separation.
⚠ Data migration nobody owns | ✅ Data Migration phase pre-populated — the #1 real-world failure scenario.
⚠ Too many Consulted = slow | ✅ Health Check shows Consulted count per role. Flags roles over-burdened with C's.
💡 Tip: Use Ctrl+F to search tasks. Freeze panes are set on all working sheets. Filter by phase using the dropdown in column A of the RACI Matrix.

## 👥 Stakeholders
👥 STAKEHOLDER REGISTER — Add all project stakeholders here. Names auto-populate RACI column headers.
ID | Full Name | Role / Title | Department | Organisation | Email | Type | RACI Code (Default) | Notes / Delegation
S01 | [Sponsor Name] | Executive Sponsor | Executive | Internal | sponsor@company.com | Internal | A | Final approver for scope, budget, go/no-go
S02 | [PM Name] | Project Manager | PMO | Internal | pm@company.com | Internal | A | Day-to-day RACI owner. Update this register on any change.
S03 | [Tech Lead] | Technical Lead / Architect | Technology | Internal | tech@company.com | Internal | R | Responsible for architecture decisions and IT delivery
S04 | [Business Analyst] | Business Analyst | Business | Internal | ba@company.com | Internal | R | Requirements, process mapping, UAT coordination
S05 | [QA Lead] | QA / Test Manager | Quality | Internal | qa@company.com | Internal | R | Test strategy, defect management, sign-off
S06 | [Finance Lead] | Finance Manager | Finance | Internal | finance@company.com | Internal | A | Accountable for data accuracy in migration & budget
S07 | [Change Manager] | Change & Comms Lead | HR / Change | Internal | change@company.com | Internal | R | Training, comms plan, adoption metrics
S08 | [InfoSec] | Information Security Officer | IT Security | Internal | infosec@company.com | Internal | C | Consulted on security, DPIA, access controls
S09 | [Vendor PM] | Vendor Project Manager | Vendor | External | vendor.pm@vendor.com | Vendor | R | Accountable for vendor deliverables and SLAs
S10 | [Vendor Tech] | Vendor Technical Lead | Vendor | External | vendor.tech@vendor.com | Vendor | R | Responsible for vendor configuration/build
S11 | [Legal / DPA] | Legal / Data Protection | Legal | Internal | legal@company.com | Internal | C | Consulted on GDPR/DPA, contracts, compliance
S12 | [End User Rep] | Business User Representative | Operations | Internal | user@company.com | Internal | C | UAT participant, process validation
S13 | [Steering Comms] | Steering Committee | Executive | Internal | steering@company.com | Internal | I | Informed at phase gates and escalations
S14 | [3rd Party Audit] | External Auditor | Audit | External | audit@auditor.com | External | I | Informed on compliance and controls

## 🎯 RACI Matrix
🎯 RACI RESPONSIBILITY ASSIGNMENT MATRIX
Project: [Name] ¦ Phase: [Current Phase] ¦ Version: 1.0 ¦ Date: [Date] ¦ RAG Status: [🟡 AMBER]
LEGEND: |  |  | R | Responsible | A | Accountable | C | Consulted | I | Informed | ⚠ ONE 'A' per row only ¦ Every task needs at least one 'R'
Phase | # | Task / Deliverable | Priority | Description / Acceptance Criteria | Sponsor | Project Manager | Tech Lead | Business Analyst | QA Lead | Finance Mgr | Change Mgr | InfoSec | Vendor PM | Vendor Tech | Legal/ DPA | User Rep | Steering Comm | Notes / Escalation Path | RACI Status
🔵 Initiation
🔵 Initiation | 1.1 | Project Charter Sign-Off | 🔴 High | Formal approval of project charter, scope, budget, and objectives | A | R | C | C |  | C |  |  | I |  | C |  | I | Sponsor A is non-negotiable. Escalate to Steering if delayed. | ✅ OK
🔵 Initiation | 1.2 | Stakeholder Register Creation | 🔴 High | Identify all stakeholders, roles, and communication needs | I | A | C | R |  |  | C |  | I |  | C |  | I | PM owns. Review with Sponsor before circulating. | ✅ OK
🔵 Initiation | 1.3 | RACI Matrix Agreement | 🔴 High | Define and obtain sign-off on roles and responsibilities across all phases | A | R | C | C | C | C | C | C | C |  |  |  | I | ⚠ This very document. Signed version = project authority. | ✅ OK
🔵 Initiation | 1.4 | Project Governance Framework | 🔴 High | Establish steering cadence, escalation path, decision authority levels | A | R | C | C |  | C |  | C | I |  | C |  | C | Governance gaps cause most escalation failures. | ✅ OK
🔵 Initiation | 1.5 | Budget Baseline & Approval | 🔴 High | Confirm approved budget, contingency reserve, and change request thresholds | A | R | C |  |  | R |  |  | I |  |  |  | I | Finance co-owns. Document approval thresholds clearly. | ✅ OK
🔵 Initiation | 1.6 | DPIA / InfoSec Review Initiation | 🟡 Med | Initiate Data Protection Impact Assessment and InfoSec onboarding | I | R | C | C |  |  |  | A | I |  | C |  | I | InfoSec A. Start early — late DPIA = project stop. | ✅ OK
🔵 Initiation | 1.7 | Vendor Contract / SOW Sign-Off | 🔴 High | Execute vendor Statement of Work, SLAs, and penalty clauses | A | R | C |  |  | C |  |  | R |  | C |  | I | Legal must review before signature. No verbal agreements. | ✅ OK
🟣 Planning
🟣 Planning | 2.1 | Project Plan & Schedule Baseline | 🔴 High | Develop integrated project schedule with milestones, dependencies, and resources | I | A | C | C | C |  | C |  | C |  |  |  | I | PM owns the baseline. Lock before sprint start. | ⚠ No R
🟣 Planning | 2.2 | Requirements Sign-Off | 🔴 High | Business requirements documented, reviewed, baselined, and approved | A | R | C | R | C | C | C | C | I | I | C | C | I | BA leads. Sponsor A. User Rep must validate. | ✅ OK
🟣 Planning | 2.3 | Architecture & Solution Design | 🔴 High | Technical architecture approved, integration points confirmed | I | C | A | C | C |  |  | C | R | R |  |  | I | Tech Lead A. Vendor co-delivers. InfoSec review mandatory. | ✅ OK
🟣 Planning | 2.4 | Test Strategy & Plan | 🟡 Med | Define test types, environments, entry/exit criteria, and defect SLAs | I | C | C | C | A |  |  |  | I | I |  | C | I | QA owns fully. Tech Lead consulted on environments. | ⚠ No R
🟣 Planning | 2.5 | Change Management Plan | 🟡 Med | Stakeholder engagement, training, comms, and resistance management plan | A: I; R: C; R: C; C: A; I: I; C: C; I: I | Change Mgr A. Sponsor to review tone and messaging. | ⚠ No R
🟣 Planning | 2.6 | Risk Register Setup | 🟡 Med | Identify, score, assign owners to top 10 risks. Baseline RAID register | I | A | C | C | C | C | C | C | R |  | C |  | I | PM maintains. All leads contribute. Review fortnightly. | ✅ OK
🟣 Planning | 2.7 | Data Migration Strategy | 🔴 High | Define migration approach, data quality rules, rollback plan, and sign-off owner | I | C | R | C | C | A |  | C | R | R |  |  | I | ⚠ Finance A for data accuracy. The #1 real-world failure point. | ✅ OK
🟠 Design
🟠 Design | 3.1 | UX / UI Design Approval | 🟡 Med | Wireframes, prototypes, and design standards reviewed and approved by business | I | C | C | A | C |  | C |  | R | R |  | C | I | BA/Business owns approval. Vendor delivers. | ✅ OK
🟠 Design | 3.2 | Integration Design Sign-Off | 🔴 High | API contracts, integration patterns, and data flows approved | I | C | A | C | C |  |  | C | R | R |  |  | I | Tech Lead A. Vendor R. No build without approved design. | ✅ OK
🟠 Design | 3.3 | Security Design Review | 🔴 High | Security controls, access model, encryption, and audit logging reviewed | I: I; A: C; C: R; C: A; R: R | R | C |  | I | InfoSec A. Mandatory gate before build commences. | ✅ OK
🟠 Design | 3.4 | Data Model & Dictionary Approval | 🟡 Med | Logical data model, field definitions, and data dictionary reviewed | I | C | C | R |  | C |  | C | R | R |  |  | I | BA leads. Finance consulted for financial data fields. | ⚠ No A
🔨 Build
🔨 Build | 4.1 | Sprint / Development Execution | 🔴 High | Agile sprints delivered per plan, code reviewed, and unit tested | I | C | R | C | C |  |  |  | A | R |  |  | I | Vendor PM A for delivery. Tech Lead technical oversight. | ✅ OK
🔨 Build | 4.2 | Infrastructure & Environment Setup | 🔴 High | Dev, Test, UAT, and Prod environments provisioned and validated | I | C | A |  | C |  |  | C | R | R |  |  | I | Tech Lead A. Vendor delivers. InfoSec reviews prod config. | ✅ OK
🔨 Build | 4.3 | Configuration & Customisation | 🔴 High | Platform configured per approved design. Deviations logged as change requests | I | C | C | C | C |  |  |  | A | R |  |  | I | Vendor PM A. Every deviation triggers change control. | ✅ OK
🔨 Build | 4.4 | Integration Build & Unit Test | 🔴 High | APIs built, connected, and unit tested. Results documented | I | C | A | C | C |  |  |  | R | R |  |  | I | Tech Lead A for integration quality. | ✅ OK
🔨 Build | 4.5 | Data Migration Build | 🔴 High | ETL scripts built, tested in Dev environment, data quality rules applied | I | C | R | C | C | A |  | C | R | R |  |  | I | Finance A for data accuracy. Run multiple dress rehearsals. | ✅ OK
🧪 Testing
🧪 Testing | 5.1 | System Integration Testing (SIT) | 🔴 High | End-to-end system test across all integrated components | I | C | R | C | A |  |  |  | R | R |  |  | I | QA A. Vendor co-responsible. Exit criteria: zero Sev-1 defects. | ✅ OK
🧪 Testing | 5.2 | Performance & Load Testing | 🟡 Med | System performance validated against agreed SLAs under peak load | I: I; A: C; C: A; C: R; R: R | R |  |  | I | Tech Lead A. Define pass criteria before test start. | ✅ OK
🧪 Testing | 5.3 | Security Penetration Testing | 🔴 High | External pen test or InfoSec scan completed and findings remediated | I | C | R |  | C |  |  | A | R | R |  |  | I | InfoSec A. Mandatory gate. No go-live without clear pen test. | ✅ OK
🧪 Testing | 5.4 | Defect Management | 🔴 High | Defects logged, triaged, assigned, tracked to closure. SLA tracked | I | C | R | C | A |  |  |  | R | R |  |  | I | QA owns defect register. Daily triage during SIT/UAT. | ✅ OK
🧪 Testing | 5.5 | UAT Planning & Execution | 🔴 High | Business users execute UAT scenarios. Issues logged and resolved | I | R | C | R | C | C | C |  | I |  |  | A | I | User Rep A for UAT execution. BA coordinates. | ✅ OK
🧪 Testing | 5.6 | UAT Sign-Off | 🔴 High | Formal business sign-off that system meets requirements and is fit for purpose | A | R | C | C | C | C |  |  | I |  |  | C | I | Sponsor A. Non-negotiable gate before go-live decision. | ✅ OK
📦 Data Migr.
📦 Data Migr. | 6.1 | Data Cleanse & Extraction | 🔴 High | Source data extracted, validated, and cleansed per migration rules | I | C | R | C | C | A |  | C | R | R |  |  | I | Finance A. ⚠ The classic failure: 'IT thought business would do this' | ✅ OK
📦 Data Migr. | 6.2 | Data Migration Dry Run #1 | 🔴 High | Full migration rehearsal in UAT environment. Reconciliation report produced | I | C | R | C | R | A |  |  | R | R |  |  | I | Run at least 2 dry runs. Finance signs off reconciliation. | ✅ OK
📦 Data Migr. | 6.3 | Data Migration Dry Run #2 | 🔴 High | Second full rehearsal. Migration window confirmed. Rollback tested | I | C | R | C | R | A |  |  | R | R |  |  | I | Timed run. Confirm cutover window fits maintenance schedule. | ✅ OK
📦 Data Migr. | 6.4 | Data Migration Sign-Off | 🔴 High | Business confirmation that migrated data is accurate, complete, reconciled | I | R | C | C | C | A |  |  | I |  |  | C | I | Finance A. No go-live without signed reconciliation report. | ✅ OK
📦 Data Migr. | 6.5 | Rollback Plan Approval | 🔴 High | Tested rollback procedure documented and approved. Trigger criteria defined | I: A; A: R; C: R; C: C; R: R | R |  |  | I | Sponsor A. Must be executable within agreed RTO window. | ✅ OK
🚀 Go-Live
🚀 Go-Live | 7.1 | Go / No-Go Decision | 🔴 High | Formal go-live decision based on exit criteria: UAT, pen test, data sign-off | A | R | C | C | C | C | C | C | C |  |  |  | C | Sponsor A. All exit criteria must be GREEN. No exceptions. | ✅ OK
🚀 Go-Live | 7.2 | Cutover Execution | 🔴 High | Production cutover executed per approved plan. Comms sent to stakeholders | I | A | R | C | C | C | R | C | R | R |  |  | I | PM commands the war room. Vendor executes. No partial cutovers. | ✅ OK
🚀 Go-Live | 7.3 | Hypercare Support Activation | 🔴 High | Hypercare team mobilised. Triage process active. SLA clock starts | I | A | R | C | R |  | C |  | R | R |  |  | I | Min 2-week hypercare. Define Sev-1 response SLA before go-live. | ✅ OK
🚀 Go-Live | 7.4 | User Training Completion | 🟡 Med | All end users trained before go-live. Attendance records signed off | I: I; A: C; C: C; R: A; R: I |  | C | I | Change Mgr A. No training completion = delayed go-live. | ⚠ No R
🚀 Go-Live | 7.5 | Post Go-Live Comms | 🟡 Med | Go-live announcement, user guides distributed, helpdesk briefed | I: I; A: C; C: C; R: A; R: I |  | I | I | Change Mgr owns. Sponsor quote in comms adds credibility. | ⚠ No R
📈 Post Go-Live
📈 Post Go-Live | 8.1 | Hypercare Issue Management | 🔴 High | Issues triaged, prioritised, and resolved within agreed SLA during hypercare | I | A | R | C | R |  | C | C | R | R |  | C | I | PM commands. Vendor SLA accountability critical here. | ✅ OK
📈 Post Go-Live | 8.2 | Benefits Realisation Tracking | 🟡 Med | KPIs measured against baseline. Benefits tracking report produced monthly | A | R | C | C |  | C | C |  | I |  |  |  | C | Sponsor A for benefits. PM coordinates measurement. | ✅ OK
📈 Post Go-Live | 8.3 | Lessons Learned Session | 🟢 Low | Structured retrospective: what worked, what failed, RACI improvements | I | A | R | R | R | C | R | C | R |  |  | C | C | All leads must attend. Output feeds next project's charter. | ✅ OK
📈 Post Go-Live | 8.4 | Project Closure Report | 🟡 Med | Final report: scope delivered, budget actual vs plan, outstanding risks | A | R | C | C | C | C | C |  | I |  |  |  | C | Sponsor A and sign-off. Archive all documents. | ✅ OK
📈 Post Go-Live | 8.5 | Contract Closure & Vendor Sign-Off | 🟡 Med | Vendor deliverables accepted, retention released, warranty confirmed | I: A; A: R; R: C; C: C; R: R |  | C |  | I | Sponsor A. Legal and Finance involved. Don't rush warranty. | ✅ OK

## 📊 Health Check
📊 RACI HEALTH CHECK DASHBOARD — Auto-calculated. Review before each phase gate.
🔴 CRITICAL CHECKS — Must be zero before phase gate
Tasks with MULTIPLE Accountables (A) | 0 | ✅ GOOD | Every task must have EXACTLY one A. Multiple A = no real owner.
Tasks with NO Accountable (A) | 1 | 🚨 FIX NOW | Unowned tasks slip. Someone must be accountable for every deliverable.
Tasks with NO Responsible (R) | 5 | 🚨 FIX NOW | No R = nobody is doing the work. Always name the doer.
📊 SUMMARY METRICS — Overall RACI completeness
Total Tasks in Matrix | 52
Tasks with valid RACI (✅ OK) | 38
RACI Completeness % | 73.08%
👥 ROLE WORKLOAD ANALYSIS — Responsibility distribution per stakeholder
Stakeholder | # Responsible (R) | # Accountable (A) | # Consulted (C) | # Informed (I) | Total Assignments | Workload Flag
Sponsor | 0 | 12 | 0 | 32 | 44 | ✅ OK
Project Manager | 15 | 7 | 22 | 0 | 44 | ⚠ Over-consulted
Tech Lead | 15 | 5 | 20 | 0 | 40 | ⚠ Over-consulted
Business Analyst | 5 | 1 | 30 | 0 | 36 | ⚠ Over-consulted
QA Lead | 6 | 3 | 22 | 0 | 31 | ⚠ Over-consulted
Finance Mgr | 1 | 6 | 16 | 0 | 23 | ⚠ Over-consulted
Change Mgr | 2 | 3 | 12 | 0 | 17 | ⚠ Over-consulted
InfoSec | 0 | 3 | 15 | 0 | 18 | ⚠ Over-consulted
Vendor PM | 24 | 2 | 3 | 15 | 44 | ✅ OK
Vendor Tech | 22 | 0 | 0 | 2 | 24 | ✅ OK
Legal/ DPA | 0 | 0 | 9 | 0 | 9 | ⚠ Over-consulted
User Rep | 0 | 1 | 9 | 1 | 11 | ⚠ Over-consulted
Steering Comm | 0 | 0 | 5 | 39 | 44 | ⚠ No R/A
📋 PHASE GATE CHECKLIST — Sign before proceeding
Phase Gate | Criterion 1 | Criterion 2 | Criterion 3 | Status | Signed By | Date
Post-Initiation | RACI signed by Sponsor | Charter approved | Stakeholder Register complete | ⬜ Not Started
Post-Planning | Requirements baselined | Architecture signed off | Risk Register active | ⬜ Not Started
Post-Design | Security review passed | Data model approved | Migration strategy agreed | ⬜ Not Started
Post-Build | All unit tests passed | Code reviewed & approved | Environments ready | ⬜ Not Started
Post-Testing | Zero Sev-1 defects | UAT sign-off complete | Pen test cleared | ⬜ Not Started
Pre-Go-Live | Go/No-Go decision logged | Rollback plan approved | Hypercare team briefed | ⬜ Not Started

## 📝 Change Log
📝 RACI CHANGE LOG — Record every change. This is your audit trail and governance evidence.
Log ID | Date | Version | Changed By | Task # / Section | Stakeholder Affected | Change Type | Previous RACI Code | New RACI Code | Reason / Justification | Approved By | Impact Assessment
CL-001 | 2025-01-15 | 1.0 | [PM Name] | 1.3 | Finance Mgr | Role Added | — | A | Finance Director added as Accountable for Data Migration after real-world failure pattern identified | [Sponsor Name] | Data migration ownership now explicit. Finance Director briefed.
CL-002 | 2025-01-20 | 1.0 | [PM Name] | 5.5 | User Rep | Code Changed | I | A | User Representative elevated from I to A on UAT execution — business must own sign-off, not observe it | [Sponsor Name] | UAT accountability strengthened. User Rep confirmed acceptance.
CL-003 | 2025-02-01 | 1.0 | [Sponsor Name] | 7.1 | Steering Comm | Code Changed | A | C | Steering Committee role changed from A to C on Go/No-Go. Sponsor retains A and sole authority | [PM Name] | Governance simplified. Steering informed post-decision.